## Slide 1: Technical challenges in the construction of the steady-state stellarator Wendelstein 7-X
Hans-Stephan Bosch
for the Wendelstein 7-X Team
Max-Planck-Institute for Plasma Physics,
Wendelsteinstr. 1, D-17491 Greifswald, Germany

## Slide 2: Outline
Introduction
Technical challenges of components
Assembly status and future work packages
Outlook: commissioning, operation
Conclusions

## Slide 3: Stellarator optimisation
Seven criteria for physics optimisation
high quality of vacuum magnetic surfaces
good equilibrium properties @ < > = 5%
good MHD stability properties @ < > = 5%
reduced neoclassical transport in 1/ -regime
small bootstrap current in lmfp-regime
good collisionless fast particle confinement
feasible modular coils

## Slide 4: Major components of Wendelstein 7-X
plasma
50 non-planar 20 planar SC coils
He pipes
254 ports
access domes and instrumentation plugins
cryostat vessel ~ 500 openings
3d-shaped plasma vessel
2500 in-vessel components
14 HTSC current leads
SC bus bar
central support ring
5.5/0.53 m major/minor plasma radius
30 m3 plasma volume
70 superconducting NbTi coils
3 T magnetic induction on axis
254 ports of 120 different types
725 t mass with 425 t cold mass
265 m2 in-vessel components
height 4.5 m diameter 16 m

## Slide 5: Outline
Introduction
Technical challenges of components
Assembly status and future work packages
Outlook: commissioning, operation
Conclusions

## Slide 6: Challenge: superconducting coil system
common superconductor:
243 single NbTi/Cu strands
cable-in-conduit conductor
soft Al-alloy for winding accuracy
He-cooling through the voids
Symmetry of the device:
five periods (modules)
2 flip-symmetric half-modules
 10 half-modules
In one half-module:
5 different non-planar coils
2 different planar coils Spulen
 70 coils of 7 types

## Slide 7: Non-planar coils

## Slide 8: Accuracy of the modular coils
All fourier components Bmn have to be smaller than 210-4 B0 (in particular B11 and B22 )
Manufacturing (soft Al-conduit)
Assembly
Careful adjustments of single coils
and coil modules has improved the
symmetry
type 2
type 1
type 4
type 3
type 5
Bmn /B0 ≈ 0.4-0.8 10-4
- systematic errors
(maintaining symmetry)
- statistical errors
(break of symmetry)
Andreeva et al.,
Fusion Engineering and Design 84(2009) 408
2 mm
1 mm
810-5
310-5

## Slide 9: The trim coils
five external saddle coils
controlling the helical magnetic axis and the magnetic edge region
water cooled copper coils
2 kA maximum nominal current
maximum sweep frequency 10 Hz
PPPL collaboration US DOE funded
fabrication of coils ongoing, 4/5 have been delivered

## Slide 10: Challenge: mechanical structure
0.0036
0.0072
0.0109
0.0146
0.0181
0.0217
0.0253
0.0289
0.0326
[m]
Magnet global ANSYS model
72 = 1/5 of the torus = 1 module
0.85M nodes
Serious overloads in support structure
No solution for narrow supports (forces up to 1.5 MN, sliding by 5 mm)
Bykov et al., Fusion Engineering and Design 84(2009) 215

## Slide 11: Final structural concept
Massive increase/modification of welds, ribs, stiffeners
Combination of welded, bolted and sliding contact elements
  Inconel bolts, inconel sleeves, and superbolt nuts
  Sliding Al-bronze elements with MoS2 coating
  Welded steel blocks where unavoidable, challenging
  welding techniques

## Slide 12: Challenge: Electric/hydraulic connection of magnets

## Slide 13: Magnet module with bus-bars

## Slide 14: Magnet module, bus-bars and cryo-piping

## Slide 15: Reality
300 steel pipes and 24 superconducting bus-bars per module
more than 500 welds and 24 superconducting joints per module
three-dimensional stellarator geometry
motion of magnets for different magnetic configurations up to
+/- 15mm
extremely limited space available in the cryostat
   - complex system of clamps and holders, stiff
  and flexible at the same time
- demanding design, engineering & manufacturing,
- complex change management
- intense metrology

## Slide 16: Challenge: welding of ports
ports cross the cryo-vacuum
to be welded to plasma vessel and outer vessel
intermediate bellows allow for small deviations only
tight space conditions in cryo-vacuum
thermal insulation has to be fitted to vessel TI
 high positioning and welding accuracy required

## Slide 17: Demanding requirements for installation of ports
1) exact positioning of port with thermal insulation
 special port assembly tool developed
2) extremely high welding accuracy required
 - extended metrology effort
- development of new welding procedures
- parallel welding/cooling to avoid distortions
- hot straigthening to correct deformations

## Slide 18: Challenge: connection of modules
  Bolting the central magnet support structure
  Assembly of connection elements between coils
  Connection of the thermal insulation of the Plasma Vessel
  Welding of the Plasma Vessel
  Connection of the Outer vessel’s thermal insulation
  Welding of the Outer vessel
  Connection of He lines and bus bars
  Installation of ports
connection of coils with +/- 0.1 mm,
welding of vessels with +/- 5 mm
required extensive developments

## Slide 19: Outline
Introduction
Technical challenges of components
Assembly status and future work packages
Outlook: commissioning, operation
Conclusions

## Slide 20: All magnet modules completed (12/10)

## Slide 21: 1st magnet module in lower shell of cryostat (10/09)

## Slide 22: 1st upper shell of cryostat assembled (11/09)

## Slide 23: Today‘s view of the torus hall
all 5 modules are completed on the machine base
assembly of the 254 ports close to completion
3 out of 5 module separation planes closed
In-vessel assembly works have started

## Slide 24: Three remaining work packages
assembly of ~ 2500 large
3d-shaped water-cooled
in-vessel components
1
assembly of 14 HTSC
current leads for seven
18kA current circuits
2
assembly of water cooling pipes, cryo supply, cable trays,
platform, heavy duty structure, diagnostics, heating systems
3

## Slide 25: In-vessel components
control coil
cryo pump
test divertor unit
baffle
wall panels
divertor closure
complete coverage of plasma vessel
2500 major components
265 m2, 34 tons

## Slide 26: Current lead assembly
assembly concept
based on port ramp design
fixing box concept tested
complex He-piping
narrow assembly space
qualified on a 1:1 mock-up
18.2 kA upside-down design
successfully tested @ 4K
Heller et al., Fusion Engineering and Design 86(3-6) 1422-1426 (2011)

## Slide 27: Periphery
cable trays
platform
NBI
Thomson bridge
diagnostics
racks
60 single projects- project teams

## Slide 28: Outline
Introduction
Technical challenges of components
Assembly status and future work packages
Outlook: commissioning, operation
Conclusions

## Slide 29: Overall schedule
assembly
completion
HHF-divertor,
diagnostics, ICRH
commissioning
commissioning
OP-1
OP-2….
2014
2015
2016
2017
2018
2019
2020
2021

## Slide 30: Integrated commissioning of Wendelstein 7-X
  All components have to bee commissioned “stand-alone” before this phase
  Integrated commissioning of the system of four major work packages
  first planning of the four work packages available
  milestones have been identified
  detailed planning has to be worked out (optimization of work steps)
Vacuum
Magnetic
field
First
plasma
Cool-down

## Slide 31: Research program
Operational phase 1 (OP-1)
inertially cooled divertor, only partial cooling of in-vessel components
up to 10 s at 10 MW, 50 s at 1 MW heating power
check of the optimisation concept of Wendelstein 7-X
development of steady state scenarios (high-density scenario with
configuration control and edge conditions suitable for divertor operation)
Operational phase 2 (OP-2)
High Heat Flux divertor, water cooling of in-vessel components
steady state at 10 MW, 10 s at 18 MW heating power
transition to high power steady state operation (30 min)
FTP/P1-23
R. Wolf
for details of the scientific program see

## Slide 32: Conclusions
Most components for Wendelstein 7-X have been finished and tested
Assembly of the device has progressed well
Schedule has been constant for the last five years
Still challenging work packages are ahead of us
Assembly will be finished in 2014
Commissioning is being prepared
A research plan for the first two years (OP-1) is being developed
W7-X programm committee will be established shortly

## Slide 33
Thank you very much!

## Slide 34: Major components of Wendelstein 7-X
plasma
50 non-planar 20 planar SC coils
He pipes
254 ports
access domes and instrumentation plugins
cryostat vessel ~ 500 openings
3d-shaped plasma vessel
2500 in-vessel components
14 HTSC current leads
SC bus bar
cryo feet
machine base
central support ring
thermal insulation MLI and He gas cooled shield